THE VERDANT PAGE

10-Day Sprint Plan

3 May – 12 May 2026  |  From Sprint 1 Complete to Launch-Ready

| 3 Phases | 18 Features | 10 Days | 0 Days Slack |
| --- | --- | --- | --- |

Sprint Overview

This plan takes The Verdant Page from its current Sprint 1 baseline to a fully self-sufficient, launch-ready platform in 10 working days. Each day has a clear focus and checkbox task list. The three phases are:

| Phase | Days | Focus |
| --- | --- | --- |
| Phase 1: Foundation | Days 1–3 | Quick wins, legal pages, email infrastructure (Resend), double opt-in, DB backup |
| Phase 2: Core Features | Days 4–7 | Full admin CMS (articles, species, portfolio), markdown editor, full-text search, Cmd+K, pagination |
| Phase 3: Polish & Launch | Days 8–10 | Analytics dashboard, newsletter broadcast UI, bookmarking, SEO audit, Lighthouse, QA, release tag |

|  | Rule: Each day ends with a working, committed build. No feature is left half-done overnight. |
| --- | --- |

Day-by-Day Plan

PHASE 1 — Foundation  (Days 1–3)

|  | Day 1 Sat 3 May ¦ Foundation - Set up automated daily PostgreSQL backup (pg_dump cron or Replit scheduled job) - Create robots.txt in frontend public/ with correct directives - Add GET /api/sitemap.xml endpoint — lists all published article and species slugs - Add JSON-LD Article schema markup inside ArticleReader page - Create a bare-bones Privacy Policy page (/privacy) — template is fine for now - Create a bare-bones Terms of Service page (/terms) - Add links to Privacy + Terms in the Footer component |
| --- | --- |

|  | Day 2 Sun 4 May ¦ Foundation - Integrate Resend SDK into the API server (install, add RESEND_API_KEY env var) - Build sendEmail(to, subject, html) utility function in api-server/src/lib/ - Trigger welcome email when a new newsletter subscriber is created (POST /api/newsletter) - Build reusable branded HTML email template (logo, green header, footer with unsubscribe link) - Add unsubscribe confirmation email when POST /api/newsletter/unsubscribe is called - Test all email flows end-to-end in Resend sandbox |
| --- | --- |

|  | Day 3 Mon 5 May ¦ Foundation - Implement double opt-in flow: on signup send confirmation email with signed token link - Add GET /api/newsletter/confirm?token=... endpoint — sets confirmed=true on subscriber - Add confirmed column to newsletter_subs table (Drizzle migration) - Only send broadcast emails to confirmed subscribers - Add /newsletter/confirmed landing page (success screen after clicking email link) - Add cookie consent banner component — shown on first visit, stored in localStorage |
| --- | --- |

PHASE 2 — Core Features  (Days 4–7)

|  | Day 4 Tue 6 May ¦ Core Features - Build Admin Article List page (/admin/articles) — table of all articles with edit/delete buttons - Add Article Create form (/admin/articles/new) — title, category, tags, status, image URL, markdown body - Wire Create form to POST /api/articles (existing endpoint, now has a UI) - Add Article Edit form (/admin/articles/:slug/edit) — pre-filled from GET /api/articles/:slug - Wire Edit form to PUT /api/articles/:slug - Gate all /admin/* routes behind the existing admin secret key check |
| --- | --- |

|  | Day 5 Wed 7 May ¦ Core Features - Embed a Markdown editor in the Article Create/Edit forms (use @uiw/react-md-editor — no backend needed) - Add live split-pane preview (editor left, rendered markdown right) using existing ArticleMarkdown component - Add Draft Preview button on edit form — opens /articles/:slug in a new tab (backend already supports status=draft) - Add image URL field with inline thumbnail preview so editors can verify the image before saving - Add word count + estimated read time display that updates as the editor content changes |
| --- | --- |

|  | Day 6 Thu 8 May ¦ Core Features - Build Admin Species List page (/admin/species) — table with edit/delete - Add Species Create/Edit form wired to existing POST/PUT /api/species endpoints - Build Portfolio Admin UI (/admin/portfolio) — list clips, add new clip form, delete button - Wire Portfolio form to existing POST /api/portfolio and DELETE /api/portfolio/:id endpoints - Add Category & Tag management UI (/admin/tags) — create and list tags, create categories - Update the admin navigation sidebar to link all new admin pages |
| --- | --- |

|  | Day 7 Fri 9 May ¦ Core Features - Implement full-text search using PostgreSQL tsvector on articles (title + content) - Add search_vector column and GIN index to articles table (Drizzle migration) - Add GET /api/articles/search?q= endpoint using ts_query - Build Global Search Overlay (Cmd+K) — modal with text input, live results, keyboard navigation - Search results show article title, category, and excerpt snippet - Implement cursor-based pagination on GET /api/articles (add cursor param, return nextCursor) - Update Articles page to use infinite scroll / Load More button with the new cursor pagination |
| --- | --- |

PHASE 3 — Polish & Launch-Ready  (Days 8–10)

|  | Day 8 Sat 10 May ¦ Polish & Launch-Ready - Build Analytics Dashboard UI (/admin/analytics) — fetch from GET /api/analytics/summary - Display: total page views, top 10 articles by views, views over last 30 days (line chart using recharts) - Display: subscriber count, subscriber growth over time - Add newsletter broadcast UI (/admin/newsletter/send) — subject + body (markdown), preview, send to all confirmed - Build POST /api/newsletter/broadcast endpoint — loops confirmed subscribers, sends via Resend - Add subscriber management table (/admin/newsletter/subscribers) — list, show confirmed status, delete |
| --- | --- |

|  | Day 9 Sun 11 May ¦ Polish & Launch-Ready - Implement article bookmarking — save article slugs to localStorage, show saved count in Navbar - Add /reading-list page that renders bookmarked articles fetched by slug - Add canonical URL meta tag to paginated article list pages (page 2, 3...) - Audit all pages for missing SEO meta — fill any gaps in react-helmet-async usage - Add Web Vitals reporting: import reportWebVitals and POST metrics to /api/analytics/vitals - Add GET /api/analytics/vitals summary to analytics dashboard - Set up uptime monitoring — configure a free external ping (e.g. UptimeRobot) on the health endpoint |
| --- | --- |

|  | Day 10 Mon 12 May ¦ Polish & Launch-Ready - Full end-to-end QA pass: create article, publish, view on site, share, search, subscribe, receive email - Run Lighthouse audit on Home, ArticleReader, and Species pages — fix any score below 80 - Verify all admin endpoints still require Bearer token after UI changes - Check RSS feed validates at validator.w3.org/feed/ - Verify sitemap.xml is reachable and lists all published content - Confirm database backup ran and the backup file is accessible - Update ALLOWED_ORIGINS env var to production domain only - Tag release: git tag v1.0.0 and push — The Verdant Page is launch-ready |
| --- | --- |

Full Feature Checklist

| Feature | Day | Category |
| --- | --- | --- |
| ☐ Automated DB backup (pg_dump cron) | Day 1 | Infrastructure |
| ☐ robots.txt | Day 1 | SEO |
| ☐ sitemap.xml endpoint | Day 1 | SEO |
| ☐ JSON-LD Article schema in ArticleReader | Day 1 | SEO |
| ☐ Privacy Policy page (/privacy) | Day 1 | Legal |
| ☐ Terms of Service page (/terms) | Day 1 | Legal |
| ☐ Resend SDK integration + sendEmail utility | Day 2 | Email |
| ☐ Welcome email on newsletter signup | Day 2 | Email |
| ☐ Branded HTML email template | Day 2 | Email |
| ☐ Unsubscribe confirmation email | Day 2 | Email |
| ☐ Double opt-in confirmation flow | Day 3 | Email |
| ☐ confirmed column on newsletter_subs | Day 3 | Database |
| ☐ Cookie consent banner | Day 3 | Legal / UX |
| ☐ Admin Article List UI (/admin/articles) | Day 4 | CMS |
| ☐ Article Create form + API wiring | Day 4 | CMS |
| ☐ Article Edit form + API wiring | Day 4 | CMS |
| ☐ Markdown editor with live preview | Day 5 | CMS |
| ☐ Draft Preview button | Day 5 | CMS |
| ☐ Admin Species CRUD UI | Day 6 | CMS |
| ☐ Portfolio Admin UI | Day 6 | CMS |
| ☐ Category & Tag management UI | Day 6 | CMS |
| ☐ Full-text search (PostgreSQL tsvector) | Day 7 | Search |
| ☐ GET /api/articles/search?q= endpoint | Day 7 | Search |
| ☐ Global Search Overlay (Cmd+K) | Day 7 | Search / UX |
| ☐ Cursor-based pagination on articles API | Day 7 | Performance |
| ☐ Infinite scroll / Load More on Articles page | Day 7 | UX |
| ☐ Analytics Dashboard UI | Day 8 | Analytics |
| ☐ Newsletter broadcast UI + endpoint | Day 8 | Email |
| ☐ Subscriber management table | Day 8 | Email |
| ☐ Article bookmarking (localStorage) | Day 9 | UX |
| ☐ /reading-list page | Day 9 | UX |
| ☐ Canonical URL on paginated pages | Day 9 | SEO |
| ☐ Web Vitals reporting | Day 9 | Performance |
| ☐ Uptime monitoring (external ping) | Day 9 | Reliability |
| ☐ Full QA pass + Lighthouse audit | Day 10 | QA |
| ☐ Production env var lockdown | Day 10 | Security |
| ☐ v1.0.0 release tag | Day 10 | Release |

Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Resend email API setup takes longer than expected | Medium | Use Resend sandbox for Day 2; real sending not needed until Day 3 double opt-in |
| Markdown editor library has styling conflicts with Tailwind | Low | @uiw/react-md-editor isolates its CSS; test in a sandbox component first |
| tsvector migration fails on large articles table | Low | Run migration in a transaction; add search_vector in a separate non-blocking ALTER |
| Day 10 Lighthouse score below 80 | Medium | Defer bookmarking/vitals to post-sprint if needed; keep QA day clear for fixes |
| No buffer day if a feature slips | High | Keep Day 10 tasks light; if Day 9 slips, cut bookmarking (lowest-impact feature) |

Definition of Done

The sprint is complete when ALL of the following are true:

- Automated daily database backup is running and verified

- Privacy Policy and Terms of Service pages are live

- sitemap.xml and robots.txt are reachable

- JSON-LD Article schema is present on all article pages

- Welcome email and double opt-in confirmation email are sending via Resend

- Admin can create, edit, and delete articles entirely through the UI

- Admin can create, edit, and delete species and portfolio clips through the UI

- Full-text search works on /articles and via Cmd+K overlay

- Article list uses cursor-based pagination

- Analytics dashboard shows page views and subscriber growth

- Newsletter broadcast can be sent to all confirmed subscribers from the admin UI

- Cookie consent banner is shown to first-time visitors

- Lighthouse scores on key pages are 80+ on Performance, 90+ on SEO and Accessibility

- All admin endpoints require Bearer token — verified with a direct curl test

The Verdant Page  |  10-Day Sprint  |  3–12 May 2026